Caddo Mills Economic Development Corporation Strategic Plan 2024-2029

Summary

The Caddo Mills Economic Development Corporation (EDC) exists to increase the tax base in Caddo Mills, Texas. This objective does not have a silver bullet solution but rather encompasses a variety of combined efforts to guide the tasks of the EDC. This strategic plan is a road map to guide the EDC’s activities over the next five  years. It is important that this strategic plan addresses the desires of the community, board, and city council.

The Caddo Mills EDC Board of Directors (EDC board) met on March 22-23, 2024. EDC board members provided the input that drives this document. Collectively the board identified strengths, weaknesses, opportunities, and threats to the city’s economy that would impact this plan.

Over the next five years, the EDC will transition from a predominately volunteer led organization to a volunteer directed and staff led organization. While that transition will inevitably have a few bumps, it is anticipated this will result in a premier organization and benefit the citizens of Caddo Mills.

Vision and Mission of the Caddo Mills EDC

This vision and mission were collectively crafted by the EDC board. It is anticipated that after adoption, the decisions of the board will be guided by this vision and mission. The Caddo Mills EDC vision and mission are presented below:

- Vision: Caddo Mills EDC fosters economic vitality while preserving our city’s distinctive character. In Caddo Mills businesses thrive and the quality of life is exceptional.

- Mission: Our mission is to foster economic prosperity and community vitality. We focus on attracting, retaining, and advancing businesses through community driven initiatives, targeted investment, and strategic partnerships.

This vision and mission was collectively crafted by the Caddo Milla EDC Board of Directors. They put much time and effort into the vision and mission. It is anticipated that after adoption, the decisions of the board will be guided by this vision and mission.

Goals, Objectives, and Strategies

Once the EDC board decided on a mission and vision, they developed the following goals to achieve the desired results.

- Business attraction and retention

- Employment

- Entertainment district

- Infrastructure enhancement

- Education

- Tourism and community development

- Entrepreneurship and innovation

After developing the goals, the board then identified objectives and strategies to achieve the goals. A description of the goals, objectives, and strategies are included on the following pages.After developing the goals, the board then developed objectives In order to reach the goals.

Goal 1:

Business Attraction and Retention

| Objectives to achieve the goal |  | Strategies to support the objective |  |
| --- | --- | --- | --- |
| 1 | Increase industry in Caddo Mills including medical, manufacturing, airport, school, and technology sectors employing 300+ people by 2029 |  | - Develop a targeted marketing campaign to attract businesses in key sectors - Acquire property in appropriate locations with a target of five acquisitions in five years (if necessary) - Downtown improvements and expansion - Focus on high potential economic development areas including 1565 corridor, 1903 corridor, FM36 corridor, and SH 66 Royse City to Caddo Mills corridor - Collaborate with surrounding areas |  |
| 2 | Attract two or more big box retailers - the first in calendar year 2025 and the second in calendar year 2026 |  | - Utilize Retail Coach - Identify broad prospects - Conduct outreach - Acquiring property (if necessary) |  |
| 3 | Retain and support existing businesses by providing resources and assistance to help them thrive |  | - Establish a business retention program to regularly engage with local businesses, identify challenges, and aid as needed |  |

Goal 2: Employment

| Objectives to achieve the goal |  | Strategies to support the objective |
| --- | --- | --- |
| 1 | Emphasize employment opportunities in the Medical, Airport Related and Industrial Arenas | - Partner with local schools, regional colleges, and vocational training centers to offer internships, apprenticeships, and workforce development programs. - Organize job fairs, training workshops, and career counseling sessions to connect local talent with employment opportunities |
| 2 | Facilitate Privately Owned Property Development | - Partner with local schools (ISD, Colleges) to offer potential internships, apprenticeships, and workforce development programs. - Organize job fairs, training workshops, career counseling to connect local talent with employers. |

Goal 3: Entertainment District

| Objectives to achieve the goal |  | Strategies to support the objective |
| --- | --- | --- |
| 1 | Create an entertainment district no later than 2026 to potentially include a movie theater (Studio Movie Grill), amphitheater, restaurants, retail, playground/family activity area, and office spaces. | - Develop a tourism marketing plan that highlights the town's natural beauty, lake, cultural heritage, and recreational opportunities. - Invest in downtown revitalization projects, public spaces, and community events to create a vibrant and attractive destination for residents and visitors alike. |

Goal 4: Infrastructure Enhancement

| Objectives to achieve the goal |  | Strategies to support the objective |
| --- | --- | --- |
| 1 | Identify and prioritize infrastructure projects that support economic development, such as transportation, utilities, and broadband access. | - Advocate for state and federal funding, grants, and public-private partnerships to finance infrastructure improvements |
| 2 | Advocate for funding and resources to improve and maintain critical infrastructure in the community. | - Advocate for state and federal funding, grants, and public-private partnerships to finance infrastructure improvements |
| 3 | Support desirable, enviable aesthetically pleasing Parks, with a Park System being in place within 5 years. | - In year one work with the city and other stakeholders to determine the location and type of park. (First Quarter 2025) |

Goal 5: Education

| Objectives to achieve the goal |  | Strategies to support the objective |
| --- | --- | --- |
| 1 | Assist the CMISD to provide appropriate skill-based education | - Support and grow the CTE Program (Airport) - Utilize grants and other mechanisms (JET Grant, Texas Workforce Commission) - Invite, facilitate and conduct quarterly meetings with the City, CMISD, EDC and Airport Board |

Goal 6: Tourism and Community Development

| Objectives to achieve the goal |  | Strategies to support the objective |
| --- | --- | --- |
| 1 | Strengthen community identity and quality of life for residents and visitors. | - Additional annual signature events, musical festivals. - Expansion of current events into multi-day. |
| 2 | Increase tourism by positioning Caddo Mills as a family-friendly destination community. | - Enhanced marketing of parks, trails, sports fields. - Development of RV friendly amenities. - Package sports tournaments with dining and shopping packages. - Invest in basic visitor infrastructure (Signage, Parking, Restrooms) |

Goal 7:

Entrepreneurship and Innovation

| Objectives to achieve the goal |  | Strategies to support the objective |
| --- | --- | --- |
| 1 | Foster a culture of entrepreneurship by providing support, mentorship, and resources to aspiring entrepreneurs. | - Establish a local mentor network, recruit mentors for local businesses and regional entrepreneurs. - Host quarterly bootcamps for planning, licensing, funding, marketing, and operations. |
| 2 | Create an ecosystem that encourages innovation and collaboration among local businesses and startups. | - Develop a shared Innovation & Collaboration Space. Monthly networking nights. Shared access to meeting rooms and training sessions. |

Strategic Plan Performance Indicators

Being the Go-To Source for Economic Development

- Be a trusted resource and convenor of intersectional meetings

- Develop accurate and timely data

- Collect Economic Development related stories

- Design and utilize appropriate incentives (when necessary)

Potential Performance Metrics

- Number of new businesses attracted to the town

- Percentage of business retention rate

- Number of workforce development programs implemented

- Percentage of infrastructure projects completed on time and within budget

Implementation Timeline

- Year 1: Focus on conducting assessments, developing partnerships, and laying the groundwork for key initiatives

- Year 2: Begin implementation of priority strategies and action plans

- Year 3: Monitor progress, evaluate outcomes, and adjust as needed to ensure alignment with goals and objectives

Budget Allocation

- Allocate funds for staffing, administration, and operational expenses

- Seek grants, sponsorships, and partnerships to supplement the budget for specific projects and initiatives

- Prioritize investments based on potential return on investment and alignment with strategic priorities

By following this strategic plan, the Caddo Mills EDC can work towards cultivating a thriving economy that benefits all members of the community.

Top of Form